## Issues
Issue IID | Title | Due Date | Time Spent (seconds) | Labels | Comment ID | Comment Body | Comment Created At
295 | PMM Slides |  | 0 | Sprint Review | 12427556 | ![image](/uploads/fed3570cff4e4cc9a60bba44768d48cf/image.png){width=1080 height=601} | 2025-08-19T13:01:46.274-07:00
295 | PMM Slides |  | 0 | Sprint Review | 12427539 | ![image](/uploads/dd6587c6e8b8e839c64b5c07ac1261bd/image.png){width=1059 height=604} | 2025-08-19T13:00:01.131-07:00
295 | PMM Slides |  | 0 | Sprint Review | 12427528 | ![image](/uploads/dd36f8fc552a6de19e0cd0413f047b05/image.png){width=1103 height=579} | 2025-08-19T12:59:14.076-07:00
295 | PMM Slides |  | 0 | Sprint Review | 12427510 | ![image](/uploads/469baf584613a9ba92ef52ad2ca12d72/image.png){width=1066 height=573} | 2025-08-19T12:58:17.708-07:00
295 | PMM Slides |  | 0 | Sprint Review | 12427476 | ![image](/uploads/ab5fe593c8941da125fb81a3e582ab5d/image.png){width=1067 height=564} | 2025-08-19T12:57:42.419-07:00
295 | PMM Slides |  | 0 | Sprint Review | 12426725 | SSOW Status Build Plan Test Plan and approach Test program baseline aligned to program objectives Test assets required plan | 2025-08-19T11:57:42.055-07:00
291 | Presentation for Jim |  | 0 | Sprint Review | 12371203 | Decision Memo for the heat frame. call this decision memo1 - Elaine has an example of this memo. | 2025-08-15T08:35:02.736-07:00
291 | Presentation for Jim |  | 0 | Sprint Review | 12371191 | Need to generate a block diagram - work with Jacob Fitch on this one. Include a ROM for costs | 2025-08-15T08:33:59.472-07:00
291 | Presentation for Jim |  | 0 | Sprint Review | 12371176 | Electrical backplane design is by me. Need to add this to the schedule. greater fidelity is needed on the SEIT Tasking as well. Braxton can weigh in on this as well to generate the CMC architecture. | 2025-08-15T08:32:19.531-07:00
289 | Update STE Plan with DVT & non ste tests |  | 0 | LOE, [SPIKE] | 12370709 | changed the description | 2025-08-15T07:33:43.212-07:00
285 | COTS SOW FOR 7774 by end of month |  | 0 | DMC, Now | 12282592 | Flores has title, Elaine has PN, Get it to Mark next for informal review. | 2025-08-12T09:06:29.515-07:00
276 | BL2.0 Build plan on paper and detailed out |  | 0 | Now | 12571278 | Ensure this includes whats being shipped and tested as kits into plano. | 2025-08-27T13:13:15.581-07:00
276 | BL2.0 Build plan on paper and detailed out |  | 0 | Now | 12143246 | This should be included in the PDR. Mallik is working on something for Thursday | 2025-08-05T07:32:44.074-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12571292 | Ensure dates match in my charts and the hw charts. | 2025-08-27T13:14:10.879-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12427590 | ![image](/uploads/c701b46558ae28ee1f2b367f7da37c5c/image.png) | 2025-08-19T13:04:16.849-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12427587 | ![image](/uploads/bdaf8be466839f626fe74e4b669f81b7/image.png) | 2025-08-19T13:04:09.996-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12427584 | ![image](/uploads/adc9c93ef37ec4368e560701033a7311/image.png) | 2025-08-19T13:04:03.889-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12427582 | ![image](/uploads/a9012aae720ff84920466d2e8d0e0936/image.png) | 2025-08-19T13:03:59.736-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12426846 | https://boeing.sharepoint.us/:p:/r/sites/SEIT_US_BLR/_layouts/15/Doc.aspx?sourcedoc=%7B9C328F94-7A36-4965-8693-91F1ED2435FA%7D&file=PDR_Template.pptx&action=edit&mobileredirect=true | 2025-08-19T12:07:56.372-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12426653 | Build Plan Test Plan and approach Test program baseline aligned to program objectives Test assets required plan | 2025-08-19T11:52:10.599-07:00
275 | PDR Charts aug 28th |  | 0 | IMS Task, Now | 12426627 | Product integration and build up approach, including draft definition of initial associated Development and Scenario Threads. Key Development/Scenario Threads included in Build Plan to foster early integration risk reduction across the product's components. Test program baseline aligned to program objectives Hardware Utilization List (HUL) is controlled and shows that it supports the programs needs (e.g., includes sufficient hardware and test assets) | 2025-08-19T11:49:12.240-07:00
273 | CTP plan with Kiran what can we do to test and approve HW ready - can we get a Fake STE up and running - how many heads do we need on this effort |  | 0 | Mauricio | 12373944 | Do they need a STE? | 2025-08-15T12:56:54.320-07:00
273 | CTP plan with Kiran what can we do to test and approve HW ready - can we get a Fake STE up and running - how many heads do we need on this effort |  | 0 | Mauricio | 12370818 | Identify the equipment needed and a testing block diagram by next week | 2025-08-15T07:52:59.938-07:00
273 | CTP plan with Kiran what can we do to test and approve HW ready - can we get a Fake STE up and running - how many heads do we need on this effort |  | 0 | Mauricio | 12118136 | changed the description | 2025-08-04T07:20:28.630-07:00
261 | Red Label SSOW iWASU Mechanical | 2025-08-08 | 0 | Mauricio, Unplanned | 12043852 | NFS3 & 10" for reference | 2025-07-30T13:25:38.196-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12309605 | Need to finalize ESS profiles | 2025-08-13T11:13:55.220-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12299487 | Need to add in ESS testing | 2025-08-12T12:28:46.231-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12155833 | Need to add APQP and have someone verify the prop markings. | 2025-08-06T08:05:34.609-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12078414 | 1) Pablo confirm my Boeing Proprietary marking. 2) Quantities with Van 3) Probe coverage from Mallika 4) Remove and/or statement 5) Fix tables per Dawn | 2025-08-01T12:22:26.665-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12036478 | Request Doc # Start from Template Write SOW Create PCR Setup Smart Bear review Link PCR to Smart Bear Review | 2025-07-30T09:33:48.946-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12017345 | https://ba-collab.web.boeing.com/ui#review:id=102212 | 2025-07-29T13:21:16.330-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12015090 | https://ba-jira.web.boeing.com/browse/WAPCR-34 | 2025-07-29T11:18:44.996-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 12014824 | changed the description | 2025-07-29T10:58:37.200-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 11932214 | One sow for all CCA's is acceptable | 2025-07-23T08:46:37.773-07:00
254 | [CM Release] Red label SSOW iWASU CCA's | 2025-08-01 | 0 | Sprint Review, Unplanned | 11931103 | Reference 10" carrier card SSOW for this effort. due date is yesterday. | 2025-07-23T07:05:53.351-07:00
251 | HUL updates per engineering actions | 2025-07-23 | 0 | Sprint Review | 11931397 | All units coming from India will be kits. I'm ordering all the Arubas needed. Need to understand the count from the HUL. | 2025-07-23T07:32:37.716-07:00
218 | SSOW for RFtesting |  | 0 | IMS Task, Mauricio | 12570891 | Following up with BCA to answer Karthi's bugs in the smart bear review. | 2025-08-27T13:05:28.072-07:00
218 | SSOW for RFtesting |  | 0 | IMS Task, Mauricio | 12155848 | This is under smart bear review. | 2025-08-06T08:07:18.557-07:00
218 | SSOW for RFtesting |  | 0 | IMS Task, Mauricio | 11760146 | Checkin on known suppliers that AID may have used. Request a statement of work as well if they have one. | 2025-07-09T13:09:28.838-07:00
218 | SSOW for RFtesting |  | 0 | IMS Task, Mauricio | 11447563 | Matrix generated and shared for iWASU. Need to update for RCU. | 2025-06-25T12:01:24.731-07:00
218 | SSOW for RFtesting |  | 0 | IMS Task, Mauricio | 11444977 | changed the description | 2025-06-25T10:09:17.143-07:00
218 | SSOW for RFtesting |  | 0 | IMS Task, Mauricio | 11433553 | CTP needs to understand TRD for RF testing ASAP | 2025-06-24T10:28:53.443-07:00
218 | SSOW for RFtesting |  | 0 | IMS Task, Mauricio | 11432964 | Need to meet with tameem pablo and Theresa to discuss the SSOW. T3 or T4? | 2025-06-24T10:00:12.956-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11908999 | CCA Data received from Abdul | 2025-07-21T09:34:33.543-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11867636 | ![image](/uploads/bbc36b809710efdac0fbbfab6bbbf984/image.png){width=501 height=150} | 2025-07-18T09:41:59.356-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11867628 | ![image](/uploads/b0230e69ad7deb2d4c423c0fe5b11ca2/image.png){width=492 height=455} | 2025-07-18T09:41:41.211-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11858789 | changed the description | 2025-07-17T11:58:39.437-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11858103 | Received test plan and industry docs needed from Sravani | 2025-07-17T11:11:36.047-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11760567 | Need to determine the EAC for this effort. | 2025-07-09T13:30:45.111-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11760517 | Gather quote from Sravani for how much this test costs. | 2025-07-09T13:25:41.310-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11646705 | CCA, plastic, gaskets, containment, connectors - on AvionX we do the FAA procedure. Mostly coupon tests, cut a cable or a CCA light those on fire. No containment testing was done. needed to cut each layer of the screen and light it. There is a doc that tells you what kind of gaskets and how to cut and mount them to burn. To use a non final board eum and quality person will sign a form at Jabel, then another at the machining location that cuts must be an approved conformity location (BCA house or Smth) sign a form there then send to test location. Figure out conformity, will need an approved test plan, must test for score with red label or get approval that its representative of red label. Acufleet 3rd party in Houston still awaiting quote. test quote from Seattle ~ 50 coupons and 10 spares 14 hours of test including test report 2 wks. 2 wks machining time plus wire testing - 29 hrs for 3 cables | 2025-07-03T09:32:51.671-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11574943 | This is an action on the meeting. Included in iWASU Engineering Actions Where are you running. When are you running what are the requirements for a program to run. This will enable me to create a spreadsheet of what must be tested and how we are conforming each piece. | 2025-06-30T09:16:40.985-07:00
185 | Flam Plan | 2025-09-03 | 0 | Next, SDRL, Unplanned | 11553800 | Need to schedule time with Brent to get details. They plan to test in September. | 2025-06-30T06:36:03.853-07:00
167 | Update STE usage in HUL per latest ims | 2025-07-03 | 0 | LOE, Sprint Review | 11717634 | Need to inch stone test efforts then feed this back into the HUL | 2025-07-08T13:05:58.865-07:00
167 | Update STE usage in HUL per latest ims | 2025-07-03 | 0 | LOE, Sprint Review | 11444988 | changed the description | 2025-06-25T10:09:32.681-07:00
167 | Update STE usage in HUL per latest ims | 2025-07-03 | 0 | LOE, Sprint Review | 11433464 | Need an export from Jaime of the MPP to start this effort | 2025-06-24T10:23:52.780-07:00
160 | [Review] Create MAC ID drawing |  | 0 | Feeds IMS Task, [SPIKE] | 12416728 | Approved on my end | 2025-08-18T13:14:44.342-07:00
160 | [Review] Create MAC ID drawing |  | 0 | Feeds IMS Task, [SPIKE] | 11760186 | Confirmed we can stay with small block. Ready for us to move forward with drawing. | 2025-07-09T13:10:38.400-07:00
160 | [Review] Create MAC ID drawing |  | 0 | Feeds IMS Task, [SPIKE] | 10848706 | Background info shared by email 5/14 | 2025-05-15T07:12:23.357-07:00
160 | [Review] Create MAC ID drawing |  | 0 | Feeds IMS Task, [SPIKE] | 10831113 | Brian needs to send info to Mauricio on background for this | 2025-05-13T11:40:22.353-07:00
143 | [Ali] Gather Aruba ICD | 2025-05-23 | 0 | LOE, SDRL, [SPIKE] | 11625914 | changed the description | 2025-07-02T10:55:53.977-07:00
143 | [Ali] Gather Aruba ICD | 2025-05-23 | 0 | LOE, SDRL, [SPIKE] | 11180514 | Obviously not. But I did receive the API docs they have | 2025-06-11T09:04:20.458-07:00
143 | [Ali] Gather Aruba ICD | 2025-05-23 | 0 | LOE, SDRL, [SPIKE] | 11101475 | Are there FAA documents that Aruba holds? | 2025-06-04T12:11:49.386-07:00
143 | [Ali] Gather Aruba ICD | 2025-05-23 | 0 | LOE, SDRL, [SPIKE] | 10998374 | An email request has been sent to Onno. Need to check for his response in the next few days. | 2025-05-27T08:40:10.468-07:00
143 | [Ali] Gather Aruba ICD | 2025-05-23 | 0 | LOE, SDRL, [SPIKE] | 10503333 | Reach out to Ali to get a definition for this document. This could be put potentially into a HSID. Could be descriptions of the CLI, API, other software spec documentation. Reach out to CTP to get these documents shared to ALI and see if that satisfies his needs. | 2025-04-16T13:27:50.814-07:00
140 | MLS Host backlog |  | 0 | DMC, Later | 10426395 | \\Mw\data\PF\03_Hardware\3U_CDS\07_Meetings\Action Items\PF_3U-CDS_Action_Items_2018-01-23.xlsx The historical spreadsheets are here: \\Mw\data\PF\03_Hardware\3U_CDS\07_Meetings\Action Items\Action Item Spreadsheets | 2025-04-10T08:09:26.401-07:00
140 | MLS Host backlog |  | 0 | DMC, Later | 10426394 | Here’s the link to FPGA backlog: https://jira-ent.web.boeing.com/secure/RapidBoard.jspa?rapidView=75397&view=planning&issueLimit=100# | 2025-04-10T08:09:20.019-07:00
116 | [Doc Release] ICD Remote Review |  | 0 | IMS Task, SDRL, [SPIKE] | 11760259 | Follow up with Mallik on when this authoring will be ready. | 2025-07-09T13:15:52.893-07:00
116 | [Doc Release] ICD Remote Review |  | 0 | IMS Task, SDRL, [SPIKE] | 11622388 | removed due date April 24, 2025 | 2025-07-02T07:52:56.772-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 12571136 | Need to find a vibe complete date. ETA this week. May know tomorrow. | 2025-08-27T13:10:40.841-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10841823 | DOuble check material type at time of planning with SuperFab. | 2025-05-14T11:51:51.430-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10214236 | Waiting on Arpan's approval of the alternate coating material. | 2025-03-25T06:30:27.103-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10214221 | [BLIS42_Requestor_Tip_Sheet.pdf](/uploads/2385c94ab1c63ec2b99287d8895be345/BLIS42_Requestor_Tip_Sheet.pdf) BLIS42 http://blis42.web.boeing.com/default.cfm?BLISPageView=staff& | 2025-03-25T06:30:00.483-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10198973 | Enter work request needed | 2025-03-24T08:26:45.155-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10149079 | Full details shared to Claudette. Waiting on Aruba arrivals. | 2025-03-20T10:16:11.586-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10142196 | changed the description | 2025-03-19T14:11:38.677-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10139393 | Flux is rosin based | 2025-03-19T11:35:49.258-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10039038 | This altered item drawing is a design drawing. Theresa will take this up with Anu to discuss process. | 2025-03-11T13:55:18.405-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10039000 | Drawing should be released and smart bear reviewed. Highlight this as a risk to prequal timing if the IMS shows an issue. Ask for a date to get an altered item drawing. | 2025-03-11T13:51:20.484-07:00
75 | Blue Label Conformal Coat Plan ~ Aruba 635 |  | 0 | LOE, Now | 10024061 | What are the antennas and keepouts | 2025-03-10T11:07:13.879-07:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 12411077 | Need to include RTV in SOW | 2025-08-18T07:21:53.120-07:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 11907101 | Mallik has an SSOW I can build from. Drawing is available. Need to update the T's & C's in there to address with supplier. Need to discuss ownership with Mallik and determine who is writing it. | 2025-07-21T07:25:23.272-07:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 11627956 | Theresa will reach out to Steve Coombs to options around analysis for an uncoated board. | 2025-07-02T13:32:19.828-07:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 10419005 | Supplier will need to provide some sort of COC. Theresa will find the name of this item. | 2025-04-09T13:19:05.586-07:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 10139366 | It is a rosin based solder | 2025-03-19T11:33:44.129-07:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9871791 | What standard are the Aruba CCAs built to (i.e. IPC 610, J-STD Class 1,2 or 3 etc..)? [It’s IPC 610. ] What kind of solder paste was used (RMA, Lead free, water soluble etc..)? [Lead free] 3) Were the CCAs cleaned during the mfg. process? a. If yes, what was the cleaning methodology (batch cleaner, hand clean, inline cleaner etc..)? [Ultrasonic Cleaning] b. How is cleanliness confirmed (i.e. Omega meter, ROSE test, ICT etc..)? [Visual inspection by 50x magnifier] | 2025-02-26T14:43:16.535-08:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9802288 | Questions have been sent to Aruba. Need to revisit next week | 2025-02-21T11:02:01.528-08:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9693483 | Hi Anu, Below are some of the questions to the attached documents 1. What is our strategy for the work? 2. Who are the audience for these documents? 3. What exactly do we want the suppliers to quote for? What are the quantities (2.1.2 is not specified), timelines, lead times, etc.? 4. Will Boeing supply the Aruba modules to the CCA house or will the CCA purchase and coat the modules? Who will be responsible for product liability (Aruba, CCA House, or Boeing)? How will final non-conformance be addressed? Some of the CCA suppliers may not want to sign up to this SSOW based on the BSCA terms and conditions since the Aruba Wi-Fi module does not belong to them and they are not responsible for anything that may go wrong during the reverse engineering process to modify the CCA component. 5. As in 2.3, 2.4 also seem not to be specific to the conformal coating work. 6. 2.3 Testing seems to refer to a CCA fully developed by the supplier but does not take into consideration that in this situation we are requesting the supplier to only do conformal coating on an Aruba module produced by Aruba. What will be the specific testing and acceptance criteria applied to this SSOW for conformal coating? 7. 2.5 refers to BAV-000179 for 10” Monitor. 8. 1.4.2 Boeing Document - Is referencing the 10” Monitor. Is this not for iWASU? 9. The provided SSOW document is trying to relay supplier responsibilities that are part of the BSCA we would sign with suppliers for Red Label and Production. For an RFP/RFQ to be issued, there must be Engineering Drawings released through the RBPI process, an engineering SOW. Do we have the drawings for this? 10. For SM to send out an RFP/RFQ, we need engineering drawings. 11. How will Boeing verify that the conformal coating has been done to Boeing specifications? 12. Who will provide the certification support through all phases described in this SSOW? 13. What is the plan B for Engineering to achieve the goal if Boeing SM team cannot find a supplier for a proposed reverse engineering request to remove CCA from the Aruba Wi-Fi module and then modify it per Boeing SSOW requirements due to liability, workmanship, warranty, producibility, terms and conditions, legal, etc. issues? With the above questions, please advise when we can meet and discuss further the SSOW. Thank you, | 2025-02-12T14:10:17.008-08:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9680159 | Double check the way I am charging this work. Should go to BEITEC CCN. | 2025-02-11T13:45:48.256-08:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9679951 | Reach out to Heath directly and see what their interest level is | 2025-02-11T13:28:08.648-08:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9661428 | changed the description | 2025-02-10T08:05:28.299-08:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9609725 | added 1h of time spent | 2025-02-06T08:03:31.434-08:00
48 | Red Label SSOW - Find supplier to handle conformal coat for Aruba 365 | 2025-08-04 | 7200 | Feeds IMS Task, [SPIKE] | 9609455 | Need to work out how ATP would be done. | 2025-02-06T07:42:35.766-08:00
47 | Xpedition install and training |  | 0 | Later, Training | 9693124 | From: Jones (US), Craig <Craig.Jones2@boeing.com> Sent: Monday, January 13, 2025 12:51 PM To: Kaddoura (US), Tameem H <tameem.h.kaddoura@boeing.com> Cc: Balasubramanian (US), Anuradha <anuradha.balasubramanian@boeing.com> Subject: Getting started with the Xpedition tool suite Hi Tameem, Boeing’s Mentor Graphics website, http://mentorgraphics.web.boeing.com, will be retired and its content is to be moved to the Electronic Products Sharepoint, https://boeing.sharepoint.us/sites/ep. I don’t know my way around this newer Sharepoint just yet, but if you click the “Electronic Product Standards” link, there is a large number of documents covering many topics. I would recommend expanding the Training group. Of the six documents listed, at least the following are worth exploring further: EP-00229 Xpedition Designer Overview: Super-high level with links to installation, training, and support options EP-00272 Intro to Xpedition Designer: EP-00273 Intro to Xpedition PDB Layout: At 500+ and 700+ pages, respectively, they’re a bit overwhelming, but these guides can run the reader through a complete design flow using the Xpedition suite. Some fraction of these documents represents the extent of my self-training on these tools. This was written against Designer VX.2.1 while we’re now on, at least, VX.2.11 – some things don’t match, but it’s usually pretty easy to figure out the current implementation. But first, anyone wishing to use Xpedition must be authorized to install it from Software Xpress. The document EP-00227 contains instructions for submitting a STAR request to obtain access to the Xpedition tool suite. If this link doesn’t work, you can search for that document number within the sharepoint. STAR Request for Xpedition.docx Hook’em, Craig Jones Avionics Hardware Engineer 469.606.7382 ¦ craig.jones2@boeing.com | 2025-02-12T13:46:03.069-08:00