## Slide 1: Procurement Timing Improvement Value Stream Mapping Project
19-December-2023
Blue Font = Updates from Todays meeting

## Slide 2: AvionX Lean Value Stream Mapping Project: AvionX Procurement Flow Time
Scope: Lab / Production Procurement (Government) Build to Print Parts
Workstreams: Developing Requirement (Need to Procure)
Creating the Buy Package
Soliciting Buy Package
Supplier Selection
Procurement Documentation
Contract Placement
Goal: Develop Lean process & standard timing for COTS, Non COTS Lab & Production Procurement Flows
Deliverables: Develop a consistent, predictable, repeatable, clearly defined process with optimized timing
        Identify current state
        Identify waste / improvement opportunities
        Create a future state map & plan to implement required improvements
        Creating aligned standard timing & inputs for Procurement activities
Team: Brandon Ady Tracy Compton Caitlin Fitzgerald Laura Piontek
Param Krishnan Noah Mass Jeff McElfresh Amy Hensley
Isaac Rosabal Kelly Weiser
Project 1
BDS & BR&T
Project 2

## Slide 3: Project 2 – AvionX COTS Lab Parts:
Identify any key stakeholders that should be involved in the process development
Quick Run through of Project 1 process flow
Update Project 1 baseline to reflect revised scope of work
Identify new opportunities
Assign opportunities to team members
Work to implement opportunities into processes and process guidance (Command Media, etc)

## Slide 4: VSM Map Future State:
DRAFT
Populate New
New Request Template
Task Time:
Total Duration:
PA
SBM
Eng
Finance
Prog Mgr
Other
Transfer
Time: 0
Transfer
Time: 0
Transfer
Time: 0
1 Hour
1 Day
Obtain list of potential suppliers (if required)
2 Hours
1 Day
Transfer
Time:
0
Develop Parts List
Identify Hazardous or EEE Parts
Transfer
Time:
0
Estimates are ROM
P
P
Proprietary
Info
Eng & SM
Together
Conduct Kickoff Meeting
1 Hour
1 Day
P
P
PROJECT 2
(Starting with Project 1 Process Map)
Look at developing a template
SRE
P
Obtain Chargelines (Material & Labor)
Confirm Chargelines Are Active (Finance)
Populate Requirements Justifcation Form (Eparts) or CAPRS Req Form
P
2 Hour
1 Day
1 Hour
1 Day
Enter order into E-Parts / CAPRS
10 Minutes
0-1 Day
Engineering Management Signoff
Property Management Signoff
P
P
E-Parts Focal
P
10 Minutes
0-1 Day

## Slide 5: VSM Map Future State:
DRAFT
Task Time:
Total Duration:
MMO Team Review (EPARTS/CAPRS as req)
Transfer
Time
Transfer
Time
Transfer
Time
TBD
1 Day
Assign PR to a Purchasing Tower (EPARTS)
TBD
1 Day
Transfer
Time
Buyer to Pull Order into their Queue (EPARTS)
TBD
1 Day – 2 Days
PA
SBM
Eng
Finance
Prog Mgr
Other
P
P
P
Bidder Board Approval
Transfer
Time
Transfer
Time
Transfer
Time
TBD
2
RFP Release
TBD
2
Proposal Received
TBD
10 – 15 Days
Non-Competitive Approval
P
P
P
Eng Finance Proposal Eval Complete
TBD
5
P
Transfer
Time
Materials Mgt Org
Supplier
P
Finance Signoff
10 Minutes
1 Day
30-39 Work Days Minimum
Questions from supplier may add time
23 Work Days Minimum
Other CAPRS Signoffs
Prog Mgr
Quality (Standardize via RSI & Commodity CodesIn)
Buyer
Planner
Have a signoff event
PROJECT 2
SRE
Pull PR from NWP Queue (CAPRS)

## Slide 6: VSM Map Future State: Non COTS Lab Procurements
DRAFT
Task Time:
Total Duration:
Transfer
Time
Supplier Down-select
TBD
2
Transfer
Time
Negotiat-ions Complete
TBD
5 – N Days
Transfer
Time
Document Procure-ment Decision
TBD
1 – 5 Days
Transfer
Time
PA
SBM
Eng
Finance
Prog Mgr
Other
P
P
P
Systems Integrity Review & Approval
Contract Award / PO Release
Transfer
Time
TBD
5 – 10 Days
TBD
1
Peer Review
Manager Review
Transfer
Time
TBD
1 – 2 Days
Transfer
Time
TBD
1 – 2 Days
P
P
P
P
Transfer
Time
Supplier acknow-ledges PO in their System
TBD
1 – 5 Days
P
Supplier
Risk
Management
Supplier
Bypass if Non-TINA
And/or if Non Govt & < $2M
17-(32+N) Work Days Minimum
How could we do this faster?
PROJECT 2
SRE

## Slide 7: Project 1

## Slide 8: 12/19/23 – Meeting Attendees

## Slide 9: Project 1 – BR&T Non-COTS Lab Parts - Open Items:
Identify Leads for Each Identified Opportunity
Work Identified Opportunities to Achieve improvement
Incorporate improvements into Timeline
Incorporate improvements into necessary process guidance / command media / AvionX Process Library

## Slide 10: Opportunity Space
Opportunities:
Hold a kickoff meeting to set expectations & inform all stakeholders.
  Create standard Kickoff Agenda
Populate a template instead of many notes / IMs back and forth
  Create the template
If we had a place to see status, showed all the steps it would cut down on e-mails (They are working on a Where’s my stuff dashboard)
Early Involvement for Long Lead Parts or Difficult to Procure Parts (During BTP Creation): Communicate to Procurement / Evaluate with Suppliers & feedback information to Engineering
Communicate the OVERALL process & timing to stakeholders early
Notify Suppliers that a PIA is being Developed
Develop & Maintain a list of Approved Suppliers by Commodity Code
Shorten the RBPI Intellectual Property Review Process from 14 days (Corporate Process / Low Likelihood) – Follow up with RBPI team
Investigate Streamlining E-Parts Approval Process – as most orders are approved. (automated depending on thresholds)
Require having delegate approvers for vacations in E-Parts
Shorten the Supplier response to PIA time to a standard 5 days.
Systems Integrity Review & Approval – Opportunity to bypass in some circumstances
Release of RBPI – Shorten from 15 days to 3 – Work with Corporate teams
Engineering & Supplier Management to Collaborate on the BOM. Eng / PM needs to get SM engaged early.
Generate Lists of Potential Suppliers Faster (than 5 days)
Accelerate RBPI Review of Supplier Responses (set up dialogue with RBPI Team)
Inform Eng Finance at time of RFP Release that the Proposal will be coming back shortly
Identify candidate program to work through the process / changes with – HOLD ABOVE UNTIL WE HAVE PROGAM IDENTIFIED
Any Steps that can be deleted / automated / done in parallel:
Requirements Justification form – Create template (currently no standard)
Location to house approved Requirements Justification Forms to scan through to see if an approved form already exists
Blue Font = Updates from Today
NEED TO ASSIGN TASKS TO PEOPLE TO PURSUE / ACHIEVE INTO NEW STANDARD WORK

## Slide 11: Future State Map
32+ Process Steps
94 78 Working Days – 153 TBD
5.5 4.5 Months Elapsed Timing

## Slide 12: VSM Map Future State:
DRAFT
Populate New
New Request Template
Task Time:
Total Duration:
PA
SBM
Eng
Finance
Prog Mgr
Other
Transfer
Time: 0
Transfer
Time: 0
Transfer
Time: 0
1 Hour
1 Day
Obtain list of potential suppliers
2 Hours
1 Day
Start & Complete the RBPI Request Process
TBD
2 Days
Obtain & Populate PIA Request Form
TBD
1 Day
Draft PIA
TBD
1 Day
Transfer
Time:
0
Issue PIA to Supplier
TBD
5 Days
Supplier Response to PIA
TBD
2 Weeks
Complete Build Print Package
Develop BOM
Develop Drawing
Identify Hazardous or EEE Parts
Develop Specifications
Transfer
Time:
0
Approve RBPI
Estimates are ROM
TBD
1 Day
TBD
1 Day
P
P
P
P
P
P
P
Intellectual Property Review
TBD
10 – 14
Days
Next Page
25-(30+N) Work Days Minimum
21 Days Minimum
Proprietary
Info
Y
N
Supplier
Time is Variable
Not included in Estimates
Eng & SM
Together
Conduct Kickoff Meeting
1 Hour
1 Day
P
P
Look at doing in parallel
Draft in parallel with RBPI and complete at same time

## Slide 13: VSM Map Future State:
DRAFT
Legal Review of Supplier Response to PIA (Optional)
Task Time:
Total Duration:
Sign PIA
Transfer
Time
Transfer
Time
Transfer
Time
Transfer
Time
TBD
10 Days
TBD
1 Day
Populate Requirements Justifcation Form
2 Hour
1 Day
Transfer
Time
Confirm Charge Number & CAM
1 Hour
1 Days
1 Hour
1 Day
Enter order into E-Parts / CAPRS
10 Minutes
0-1 Day
Transfer
Time
Engineering Management Signoff
Transfer
Time
Property Management Signoff
PA
SBM
Eng
Finance
Prog Mgr
Other
P
P
supplier
legal
P
P
P
P
E-Parts Focal
P
Prog Mgr /
CAM
From Prior Page
Review & Update PIA
10 Minutes
0-1 Day
Release of Boeing Proprietary Info
TBD
3 Days
P
Legal
22-52 Work Days Minimum
17 Work Days Minimum
Look at pulling earlier
Look at pulling earlier
Do after signed PIA

## Slide 14: VSM Map Future State:
DRAFT
Task Time:
Total Duration:
MMO Team Review (EPARTS)
Transfer
Time
Transfer
Time
Transfer
Time
TBD
1 Day
Assign PR to a Purchasing Tower (EPARTS)
TBD
1 Day
Transfer
Time
Buyer to Pull Order into their Queue (EPARTS)
TBD
1 Day – 2 Days
PA
SBM
Eng
Finance
Prog Mgr
Other
P
P
P
Bidder Board Approval
Transfer
Time
Transfer
Time
Transfer
Time
TBD
2
RFP Release
TBD
2
Proposal Received
TBD
10 – 15 Days
Non-Competitive Approval
P
P
P
Eng Finance Proposal Eval Complete
TBD
5
P
Transfer
Time
Materials Mgt Org
Supplier
P
Finance Signoff
10 Minutes
1 Day
30-39 Work Days Minimum
Questions from supplier may add time
23 Work Days Minimum
Other CAPRS Signoffs
Prog Mgr
Quality
Buyer
Planner
Have a signoff event

## Slide 15: VSM Map Future State: Non COTS Lab Procurements
DRAFT
Task Time:
Total Duration:
Transfer
Time
Supplier Down-select
TBD
2
Transfer
Time
Negotiat-ions Complete
TBD
5 – N Days
Transfer
Time
Document Procure-ment Decision
TBD
1 – 5 Days
Transfer
Time
PA
SBM
Eng
Finance
Prog Mgr
Other
P
P
P
Systems Integrity Review & Approval
Contract Award / PO Release
Transfer
Time
TBD
5 – 10 Days
TBD
1
Peer Review
Manager Review
Transfer
Time
TBD
1 – 2 Days
Transfer
Time
TBD
1 – 2 Days
P
P
P
P
Transfer
Time
Supplier acknow-ledges PO in their System
TBD
1 – 5 Days
P
Supplier
Risk
Management
Supplier
Bypass if Non-TINA
And/or if Non Govt & < $2M
17-(32+N) Work Days Minimum
How could we do this faster?